## PREL
CONSTRUCTION OF UPPER KALAWAZE BOREHOLE IN TURKANA COUNTY
ITEM NO. | ITEM DESCRIPTION | UNIT | QTY | RATE (KSHS) | AMOUNT
KSHS
BILL NO.01 PRELIMINARIES AND GENERALS
A | Allow provision for insurance in accordance with Clauses 21, 23 and 24 of the Conditions of Contract II for Drilling | ITEM | 1
B | Allow provision for power and water supply | ITEM | 1
D | Provide sign board for the work as required by law | ITEM | 1
TOTAL (Carried to Summary)

## PS
|  | UNIT | QTY | RATE KSHS | AMOUNT
ITEM | DESCRIPTION |  |  |  | KSHS | CTS
BILL NO. 2 PROVISIONAL SUMS
The tender shall include in his/her tender the following Provisional Sums to be expended in whole or part thereof at the discretion and on instructions of the Project Manager.
A. | Allow a Provisional sum of Kenya Shillings One Million (Kshs. 1,000,000/=) for Project Supervision and Administrative expenses. | ITEM | 1 | 1000000 | 1000000 | 0
B. | Allow a provisional sum of Kenya shillings One Million Five Hundred Thousand (Kshs1,500,000) to utilized in whole or part for construction of access road, sanitary facilities, environmental retsoration and other utilities as directed the PM | ITEM | 1 | 1500000 | 1500000 | 0
C. | Allow for attendance | 15% | 1 | 285000 | 285000 | 0
| TOTAL CARRIED TO SUMMARY |  |  |  | 2785000 | 0

## Drilling
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
|  |  |  | (KSHS) | KSHS | CTS
BILL No. 3: DRILLING, DEVELOPMENT and TEST PUMPING TOTAL DEPTH: 130M
A | Mobilization, transportation of machinery, erection of camps and sanitary facilities and demobilization | LS | 1
B | Mobilization from site to site within the same zone | LS | 1 | 150000 | RATE ONLY
C | Mobilization from one zone to the other zone | LS | 1 | 250000 | RATE ONLY
D | Erecting and dismantling of drilling equipment and other machinery at the site. | LS | 1
E | Drilling of borehole of minimum diameter 205mm through all types of strata including disposal of excavated materials, taking any remedial measures to overcome caving-in, or over drilling to accommodate sloughed material and keeping drilling records as specified between ground level and 150 metres below ground level. | M | 130
F | Supply and install 152 mm internal diameter plain steel casings in the borehole. | M | 90
G | Ditto A1.5 but 152mm internal diameter slotted steel casings. | M | 40
H | Allow for taking samples of drill cuttings at two (2) metres intervals | LS | 1
I | Supply and insert gravel pack (rounded 2-4 mm diameter). | Tons | 10
J | Grout between the casing and the borehole for top ten (10) metres. | LS | 1
K | Physical development of the borehole including inserting and removal of development equipment; | HR | 24
L | Chemical development of the borehole including inserting and removal of development equipment; | HR | 8
M | Undertake Constant Discharge Test as specified (24 hours for actual test pumping and 8 hours for insertion and removal of test pumping equipment) | HR | 32
N | Undertake water Level observation and record recovery. | HR | 8
O | Carry out borehole sterilization | LS | 1
P | Install wellhead, well cap serial number and cement slab of dimensions 1.0x1.0x1.0 metres around the wellhead. | LS | 1
Q | Supply of water and drilling fluids for drilling operations and field camp | LS | 1
R | Take water samples for laboratory analysis (1 No. sample for Bacteriological and 1 No. for Chemical each 15 litres). | LS | 1
S | Allow for making good and surface reinstatement at the borehole location to the Project Manager’s satisfaction. | LS | 1
| TOTAL CARRIED TO SUMMARY |  |  |  | 0 | 0

## Solar Pump
Item | Equipment Description | Unit | QTY | Rate | AMOUNT
| BILL No.4 SUPPLY AND INSTALLATION OF GRUNDFOS SOLAR PUMP (PUMP TYPE SQF 2.5-2 with DISCHARGE of 2.6M3/hr Powered by 0.8KW motor Assumed head HEAD=70m Solar PANNELS No. of panels=9each of capacity of 125W |  |  |  | KSHS | CTS
A | Grundfos SQF 2.5-2 complete with motor | No. | 1
B | Solar panels capacity 80watts | No. | 11
C | Solar pump control unit | No. | 1
D | 6mm2 4 core flat submersible drop cable | m | 120
E | 6mm2 4 core underground cable | m | 15
F | 1¼'' adapter set | No. | 1
G | 1¼'' by 2" adapter | No. | 1
H | 1¼'' PVC pipe 3m length | No. | 42
I | 25mm airline pipes | No. | 15
J | Splicing kit | No. | 1
K | Cooling sleeve | No. | 1
L | 1¼'' x 6" borehole cover complete with sundries | No. | 1
M | 15mm2 x 2 core underground cable float switch | m | 60
N | Float switch | No. | 1
O | Earth rod complete with clamp and earth cable | No. | 1
P | Water meter |  | 1
Q | Module support structure | m | 6
R | Installation accessories | Sum | 1
S | Installation labour and transport | Sum | 1
T | Supply and lay 2"Ø UPVC class D for rising main | m | 450
U | Excavate trench for pipe lying not exceeding 450mm depth and backfill | m | 450
V | Transport and labour for solar panel | LS | 1
W | Plastic Water tank-10000lts | 1 | 1
| Provide pipe line anchors | Unit Rate | 1
TOTAL CARRIED TO SUMMARY
Note on B22: DRSPIT:
Note on G22: DRSPIT: Should be removed what do you think

## Tank Plat Form
ITEM | DESCRIPTION | UNIT | QTY | RATE (KSHS) | AMOUNT
[5 empty] | KSHS | CTS
BILL NO.05: PLASTIC TANK AND RAISED PLATFORM
SUBSTRUCTURES
RAISED PLAFORMS
(ALL PROVISIONAL)
A | Excavate for columns footing not exceeding 1.50m deep. | CM | 13.5
Plain Concrete 1:4:8 mix in:
B | 50 mm blinding bed under columns footing | CM | 0.45
Reinforced Concrete 1:2:4- 20mm gauge mix in
C | Columns bases | CM | 4.5
D | Columns | CM | 0.75
Reinforcement
High Tensile Steel Reinforcement to B.S. 4483
E | Y8 | KG | 20.9
F | Y16 | KG | 287.9
SUPERSTRUCTURES
MILD STEEL TO B.S. 449
Structural steel welded & Bolted joints
Columns /staircases bases plate
G | 200x200x10.0mm | NO | 4
H | 150x150x4.0mm | NO | 16
I | 200x200x6.0mm | NO | 4
J | 200x200x6.0mm | NO | 4
K | Base Bolts 200m long 20mm dia Hold down bolts. | NO | 16
L | 12mm dia ordinary bolts. | NO | 20
LADDER
A | 32x1.5mm dia CHS pipes | NO | 15
B | 50x2.0mm dia CHS pipes | LM | 8.4
COLUMNS
C | 100x100x4.0mm SHS | NO | 4
PLATFORM FLOOR
D | 150x100x3.0mm RHS bearers beam | NO | 9
E | 203x133x25UB | LM | 8.4
F | 4mm chequered plate | SM | 40
SIDE RAILS
G | 50x50x2.0mm SHS | NO | 32
H | 25x1.2mm dia CHS pipes | LM | 50.4
I | 75x75x6.0mm Angle section | NO | 8
J | 75x75x6.0mm Angle section | NO | 1
BRACING ANGLES
K | 75x50x4.5mm Angles,100mm width | NO | 24
PLASTIC TANK
L | 10,000 litres plastic tank | NO | 1
PLUMBING
M | Supply and lay 32mm PPR PN 20 to water kiosk and cattle trough | M | 100
N | Supply and fix 32mm T-junction on supply main | NO | 1
TOTAL FOR TANK INSTALLATION CARRIED TO SUMMARY

## W. Kiosk
|  | UNIT | QTY | RATE KSHS | AMOUNT
ITEM | DESCRIPTION |  |  |  | KSHS | CTS
BILL NO.06
SUBSTRUCTURES
WATER KIOSK
(ALL PROVISIONAL)
A | Excavate oversite to remove vegetable soil average 150mm deep;wheel and deposit on site n.e. 100M away in permanent spoils heaps | SM | 11.6
B | Excavate for strip footing not exceeding 1.50m deep. | CM | 8
Disposal
C | Back filling selected excavated materials around foundation. | CM | 5.28
Hardcore
D | 250mm thick filling: deposit, spread, level and compact: to receive blinding | SM | 12.9
E | 50mm murram blinding to surface of hardcore. | SM | 12.9
F | Polythene sheet damp proofing;500gauge | SM | 12.9
Anti-Termite Treatment
G | Chemical anti-termite treatment executed by Rentokil Laboratoties Limited or equal and approved pest control firm under a ten year gurantee, applied to surface of excavation and floor | SM | 12.9
Plain Concrete 1:4:8 mix in:
H | 50 mm blinding bed under strip footing | CM | 0.3
Reinforced Concrete 1:2:4- 20mm gauge mix in
| 150 mm floor slab | SM | 12.9
I | Strip Footing | CM | 1.1
Reinforcement
High Tensile Steel Reinforcement to B.S. 4483
Mesh Fabric Reinforcement to B.S.4483
J | Mesh reinforcement reference A 142 weighing 2.22kg per square metre laid in bed with 300mm side and end laps (Measured net allow for laps) | SM | 12.9
K | Y8 | KG | 11
L | Y10 | KG | 16.5
MASONRY
Medium quarry dressed stone walling in cement and sand (1:3)mortar:20 gauge x 25mm wide hoop iron reinforcement and column-wall ties in every alternate course: to
M | 200mm walling in Foundation | SM | 13.2
ELEMENT NO-02
SUPERSTRUCTURE
MASONRY
A | Medium quarry dressed stone walling in cement and sand (1:3)mortar:20 gauge x 25mm wide hoop iron reinforcement and column-wall ties in every alternate course: to 200mm walling | SM | 17.6
Reinforced Concrete 1:2:4- 20mm gauge mix in
B | Rings Beams;300x200 | CM | 0.55
Sawn formwork to
C | sides and soffits of beams | SM | 5.3
Reinforcement
High Tensile Steel Reinforcement to B.S. 4483
D | Y8mm Bars | KG | 13.5
E | Y12mm Bars | KG | 31.3
Sawn Treated Cypress
G | 75mmx50mm Braces, ties, strut, and posts | L.M. | 23.8
H | 100 x 50mm wall plate | L.M | 8.8
Wrought Treated Cypress
I | 225mm x25mm Fascia or barge board | L.M | 13.6
Roof Covering 28 Gauge Corrugated ‘Resincot’ Iron Sheeting and Accessories
J | Roofing Covering with 1 ½ Corrugation side laps nailed to timber Purlins with galvanized roofing nails with rubber washers (Measured out and allow for laps) | S.M | 11.6
FINISHES
DOORS
K | Single door; 50 mm thick ; 1000 x 2100 mm high | NO | 1
WINDOWS
Standard door complete with hinges,stays,fasteners,permanent vent with mosquito gauze and sheet metal hood ect assembled and fixed to surround including cutting and pinning lugs to concrete or blockwork surround and bedding frame in cement and sand mortar (1:4),steel casement door comprising 40x25x3mm stiles,bottom &top rail,&4No intermediate rails all primed with red oxide
L | 1500x1200mm with two sides hanglights;one fixed bottom light and one fixed lights | NO | 1
WALLINGS FINISHES
M | 15mm lime plaster:steel trowelled finish:on blockwork:to
N | Walls(internals) | SM | 14.5
O | Prepare and apply three coats approved emulsion paint to: | SM | 14.5
P | Walls(external walls)
Q | Extra over walling for medium chisel dressing | SM | 14.5
FLOOR FINISHES
A | 50mm thick floors screed | SM | 11.6
Plumbing (Supply and fix the following)
B | ¾” GI pipe | No. | 1
C | ¾” Gate Valve (Peggler) | No. | 1
D | ¾” Bend | No. | 3
E | ¾” Elbow | No. | 4
F | ¾ Tee equal | No. | 3
G | ¾” Union | No. | 1
H | ¾“ Stop Cork (Peggler) | No. | 3
I | ¾” Hexagonal nipple | No. | 10
J | ¾” Sockets | No. | 2
K | PVC end-caps 2” | No. | 2
L | PVC end-caps 1½” | No. | 2
M | PVC Tee equal 2” | No. | 2
N | Ditto ½” | No. | 2
O | Reducing socket 2” x ¾” PVC | No. | 2
P | Ditto 1 ½” x ¾” | No. | 2
Q | PVC Adapter ¾” | No. | 2
TOTAL CARRIED TO SUMMARY

## Catt. Trough
ITEM | DESCRIPTION | UNIT | QTY | RATE (KSHS) | AMOUNT
[5 empty] | KSHS | CTS
BILL NO.07
WATER TROUGH
SUBSTRUCTURES
(ALL PROVISIONAL)
A | Excavate oversite to remove vegetable soil average 150mm deep;wheel and deposit on site n.e. 100M away in permanent spoils heaps | SM | 72.1
Hardcore
D | 250mm thick filling: deposit, spread, level and compact: to receive blinding | SM | 72.1
E | 50mm murram blinding to surface of hardcore. | SM | 72.1
Anti-Termite Treatment
F | Chemical anti-termite treatment executed by Rentokil Laboratoties Limited or equal and approved pest control firm under a ten year gurantee, applied to surface of excavation and floor | SM | 72.1
Damp-Proof Membrane
G | 500mm Gauge polythene damp-proof membrane laid on blinded hardcore with 100mm folded side and end laps (measured net-allow for laps) | SM | 72.1
Reinforced Concrete 1:2:4- 20mm gauge mix in
H | 150 mm floor slab | SM | 72.1
I | 150 mm thick Rc Walls | CM | 3.85
Reinforcement
High Tensile Steel Reinforcement to B.S. 4483
Mesh Fabric Reinforcement to B.S.4483
J | Mesh reinforcement reference A 142 weighing 2.22kg per square metre laid in bed with 300mm side and end laps (Measured net allow for laps) | SM | 159.5
PLUMBING
K | Supply and fit 32mm gate valve and connect to supply main | NO | 1
L | Supply and fit Ball Valve | NO | 1
STEEL COVER
M | Access cover | NO | 1
TOTAL CARRIED TO SUMMARY

## Fence
ITEM NO. | ITEM DESCRIPTION | UNIT | QTY | RATE (KSHS) | AMOUNT
[5 empty] | KSHS | CTS
BILL NO. 8 FENCE
FENCING
(ALL PROVISIONAL)
A. | Clearing the site of bushes/trees | SM | 1000
B | Excavate for fencing poles bases from exsisting ground level and not exceeding 1.50m deep.(225 x 225x500mm deep holes) | NO. | 48
Concrete Work
Mass concrete 1:4: 8-
C | 50 mm blinding bed under holes for fencing posts | CM | 0.2
Reinforced Concrete 1:2:4- 20mm gauge mix in
D | 225x225x450 Bases for Angle columns sections | CM | 1.5
MILD STEEL TO B.S. 449
Structural steel welded & Bolted joints
E | 75x75x4.5mm Angle column section (Length 2350mm spaced at 3 m c/c) | NO | 48
G | 75x75x5.0mm angle section for bracing at corners and at every 30m span (Length 3600mm ) | NO | 12
GATE
K | Excavate for sides columns poles bases from exsisting ground level and not exceeding 1.50m deep.(225 x 225x500mm deep holes) | NO. | 4
Concrete Work
Mass concrete 1:4: 8-
M | 50 mm blinding bed under holes for fencing posts | CM | 0.1
N | Reinforced Concrete 1:2:4- 20mm gauge mix in
| 225x225x450 Bases for SHS columns | CM | 0.1
MILD STEEL TO B.S. 449
Structural steel welded & Bolted joints
O | 100x100x4.0mm SHS column (Length 2000mm) | NO. | 3
P | 75x75x3.0mm SHS | LM | 28.5
Q | 50x50x3.0mm SHS | LM | 21
FENCING WIRE
Barbed wire
R | Supply and fix Ngombe Double strand Barbed wire 610mtrs, around the perimeter;or equivalent | NO | 2
CHAIN LINK
S | Supply and fix 3.0mm chain link twisted 3 times at the ends | SM | 234
T | Bind the chain with a binding wire | ROLLS | 2
TOTAL CARRIED TO SUMMARY

## SUMMARY
SUMMARY
Item | Description | Amount
|  | Kshs | Cts
A. | BILL NO. 01 PRELIMINARIES
B. | BILL NO. 2 PROVISIONAL SUMS | 2785000 | 0
C. | BILL NO. 3: DRILLING, DEVELOPMENT and TEST PUMPING |  |  | 8
D. | BILL NO.4: SUPPLY AND INSTALLATION OF GRUNDFOS SOLAR PUMP
E. | BILL NO.5: INSTALLATION OF PLASTIC TANK ON MILD STEEL PLATFORM AND LAYING MAIN PIPE
F | BILL NO. 6: CONSTRUCTION OF WATER KIOSK
G | BILL NO.7: CONSTRUCTION OF CATTLE TROUGH
H | BILL NO. 8 FENCE
TOTAL CARRIED TO GRAND SUMMARY

## G SUMMARY
ITEM | DESCRIPTION | OFFICIAL USE |  | TENDERER’S USE
AMOUNT
GRAND SUMMARY
|  | KSH | CTS | KSH | CTS
A. | TOTALS FOR THE PROPOSED DRILLING AND DEVELOPMENT OF UPPER KALAWAZE BOREHOLE
B. | Contingency Sum (10%)
CONTRACT SUM CARRIED TO FORM OF TENDER
AMOUNT IN WORDS: ………………………………………………………………………
NAME OF TENDERER: ………………………………………………………………………
ADDRESS: ……………………………………………………………………………………..
SIGN: ……………………………………………………………………………………………
DATE: …………………………………………………………………………………………
WITNESS NAME: …………………………………………………………………………….
ADDRESS: ……………………………………………………………………………………
SIGN: ………………………………………………………………………
DATE: ……………………………………………………………………….